## Change Request
12 | Date : 30-10-2021 - Time : 08:50
SN | Change Request | Status | Tausif Remark | Remark
1 | Sales & Invoice-->Quotation Creation Form - unit price can be editable but should not accept less than minimum selling price which is set in the product card | Done
2 | Sales & Invoice-->Invoice Creation Form - when you try to add a product where the dropdown of a product is not showing all the product listed in product list. |  |  | its coming as per warehouse and stock mgt. count
3 | Requesting to please call me will show you the demonstration of points listed in Section 11 ( 2 and 3 ) and Section 10 ( 1 and 3 )
4 | When you create Invoice the product inventory is not getting deducted as the product is sold, please check this | Done
11 | Date : 26-10-2021 - Time : 09:19
SN | Change Request | Status | Tausif Remark | Remark
1 | Sales & Invoice-->Quotation Form - please change the header from "Sales & Purchases / Sales & Invoices / Quotation No#" to " Sales & Purchases / Sales & Invoices / Quotation" as above this we are showing the Quotation Number. | Done | Done
2 | Sales & Invoice-->Quotation Creation Form - when you add the customer in the pop up section the customer list is not showing and accordingly the customer branch also |  |  | not understand what u saying
3 | Sales & Invoice-->Invoice Creation Form - when you add the customer in the pop up section the customer list is not showing and accordingly the customer branch also |  |  | not understand what u saying
4 | Sales & Invoice-->Invoice Creation Form - unit price can be editable but should not accept less than minimum selling price which is set in the product card | Done | Done
10 | Date : 16-10-2021 - Time : 08:43
SN | Change Request | Status | Tausif Remark | Remark
1 | in Stock Management / Sock Movement / Stock Correction please add the search box in such a way that any product that are searched to add product can be searched by product name , product ref id or barcode number | Done | Not Done | Not done , please call me
2 | Creat Invoice From - User can be able to edit Unit Pricing , note the unit price can not be less than Minimum Selling Price | Done | Done
3 | There are some correction that have to be made in Created Invoice View
9 | Date : 12-10-2021 - Time : 09:20
SN | Change Request | Status | Tausif Remark | Remark
1 | Add Warehouse Form - when you click "edit" or "add" wharehouser details and after making the changes when you save it make the changes , then it does not exit to wharehouse list, where as its coming back to the same "Add Warehouse form" it should not come back to the form | Done | Done
2 | Warehouse List - please rename "Sr No." to "Warehouse Reference No" in the Warehouse List | Done | Done
8 | Date : 11-10-2021 - Time : 20:11
SN | Change Request | Status | Tausif Remark | Remark
1 | Settings -> Company - in Orginazation card "Branches & Warehouse" tab please fix the list of "country" its not picking from the DB | Done | Done
2 | User Settings-->User List - please note that the list is not taking the user details from the DB, please check that and fix it. |  |  | it`s coming from sys_erp_adm_user table
3 | Hide the Super Admin from the list of HRM "Staff Details / Staff List " | Done | Done
4 | Add Product Form - in this you can see there is "Desired Optimal Stock" twice | Done | Done
7 | Date : 11-10-2021 - Time : 09:26
SN | Change Request | Status | Tausif Remark | Remark
1 | Create a DB Table for Customer Branches ( TB Name : crm_cust_details_branch ) which will have all the detail of the Customer additional branches |  |  | Let me know fields of table and mockup
2 | Create a DB Table for Vendors & Suppliers Branches ( TB Name : vndr_details_branch ) which will have all the detail of the Vendors & Suppliers additional branches |  |  | Let me know fields of table and mockup
Note the Branches table should me same as wharehouse but remove the reference of the warehous , not rename the warehoues in these tow table as branches
3 | remove the unwanted table from the DB |  |  | Only below table are not used anywhere in whole application other all tables are used tbl_countries-old,tbl_states-old
4 | If there is one warehouse then after the login it should not prompt for selecting branch/warehouse | Done | Done
5 | Settings -> Company - in orginazation details the "Country" , "State / Province" Db is not linked please check that | Done | Done | It`s Coming from db
6 | Settings -> Company - in orginazation PO Bos is not showing the same value entered at the top highlight card | Done | Done
7 | Duplicates cannot be created in Contact's , Customer, Vendor and any tags / catogeries |  |  | What duplicate? email or mobile number
6 | Date : 10-10-2021 - Time : 16:56
SN | Change Request | Status | Tausif Remark | Remark
1 | Invoice Creation - please note that if the "Payment Type" selected at whatever days then the "Due Date" will be set accordingly e.g. if the invois is generated on 10-10-2021 "Payment Type" Selected 7 days then the "Due Date" should be 17-10-2021 | Done | Done
2 | Vendor & Suppliers Form - Note that the "Vendor / Supplier" select should be "Yes" as Default , currently is "No" and move that above the "Prospect / Customer" | Done | Done
3 | Vendor & Suppliers Form - Note that the "Prospect / Customer" select should be "Nor Prospect, Nor Customer" as Default , currently is "Customer" | Done | Done
4 | Vendor & Suppliers Form - Note that the "Status *" is showing some error it should be a "Active" or "In-Active", check for Customer creation form is Active & In-Active is coming from DB | Done | Done
5 | Product List - The product discription hover is not working, please check that and fix it.
6 | Product List - Selling price should have "/- QAR" if the currency is set as QAR in "Finance & Accounts-->Accounting-->Multi Currency". | Done | Have to check the "Finance & Accounts-->Accounting-->Multi Currency".
7 | Finance & Accounts-->Accounting-->Multi Currency - please make a multi currency page with a default currency |  |  | Send mockup
8 | Add Product Form - all barcode types are not listed |  |  | Other type of barcodes are not working properly that`s why i had disabled those.
9 | Add Product Form - note in barcode value its only taking numeric only it should be taking alpha numeric both. | Done | Done
10 | Add Product Form - once you save a a product from "Add New Product" form then it should automatically redirect to "Product List" page. | Done | Done
11 | Product List - when you export a "Product List" to excel file its not downloading with all the fields please check it and fix it.
12 | Add Vendor & Suppliers Form - please move the "Office Address " box above "TAX & Other Leagal's " | Done | Done
13 | Vendor & Suppliers List - please remove the column "State" from the listing keep only "Country" and "City" | Done | Done
5 | Date : 10-10-2021 - Time : 09:43
SN | Change Request | Status | Tausif Remark | Remark
1 | Top right hand site the user beside user name you can see some code's "profile-user" | Done | Done | Send screenshot for same / this is done
2 | User Profile Drop Down - kepp only the "User Profile" & "Log Out" button and remove the "Settings" Button | Done | Done
3 | Customer Card - when you click "edit" customer details and after making the changes when you save it make the chnages and get exited to customer list, where as it should be coming back to the same customer card | Done | Done
4 | Customer Card - in customer card "Delivery Note" when you click "Add Delivery Note" it should only create delivery note for the Invoice created for that customer. | Done | Done
4 | Date : 09-10-2021 - Time : 21:43
SN | Change Request | Status | Tausif Remark | Remark
1 | Vendor & Suppliers Card - in "Vendor & Suppliers Card" ---> there is "Contact Persons" Tab please add "Add Contact" button which should add the contact in CRM-->Contact Book and automatically linked with that company from which the add contact was clicked, also it should auto fill that company default detail but those can be edited |  |  | We had added contact book only for customer not for vendor
2 | Customer Card - in "Customer Card" ---> there is "Contact Persons" Tab please add "Add Contact" button which should add the contact in CRM-->Contact Book and automatically linked with that company from which the add contact was clicked, also it should auto fill that company default detail but those can be edited | Done
3 | Vendor & Suppliers Card - the "Branch & Shipping Address" tab is showing the ERP Orginazation Warehouse and shipping address , please fix this Tab should have the list of Branch & Shipping Address of that vendor also add a "Add Branch & Shipping Address" |  |  | Not getting this point
4 | Customer Card - the "Branch & Shipping Address" tab is showing the ERP Orginazation Warehouse and shipping address , please fix this Tab should have the list of Branch & Shipping Address of that vendor also add a "Add Branch & Shipping Address"
5 | Customer Card - please make the the listing format as "Customer Card ---> Contact Persons" I mean by this the layout.
6 | Add Customer Form - please move the "Office Address " box above "TAX & Other Leagal's " | Done | done
7 | Customer List - please remove the column "State" from the listing keep only "Country" and "City" | Done | done
8 | in Every form please check if the "Country*" drop down has the search box
3 | Date 08-10-2021 - Time 19:27
SN | Change Request | Status | Tausif Remark | Remark
1 | Product List - Please check the import and export of product list, it should work perfectly | Done |  | Have to check
2 | Add Product Form - Please make the change for the Add Product Form as show in the mockup ( File Name : product-add.html ) | Done | done
3 | Add Product Form - "Reference Number" should rename as "Reference ID / Number" but keep intact as in DB | Done | done
4 | Add Product Form - "Barcode Value" should auto taken same as the Product "Reference Number" | Done | done
5 | Add Product Form - "Barcode Type" the default value has to be set in the "Barcode Settings" | Done |  | Have to check
6 | Add Product Form - remove "Virtual Stock " & "Physical Stock " as this will be managed by the stock management module | Done | done
7 | Add Product Form - hide the weight and dimentions of the product in Add Product Form, we will use this in future | Done | done
8 | Product Card - the product card mockup is shown in the file ( File Name : product-FST112-12W.html ) note : ignore the logo ist just the mockup | Done | done
9 | Product Card - remover the "Statistics" Tab from the product card | Done | done
10 | Product Card - the currency has to be auto added "/- QAR" this will come with from the primary currency selected in finance module | Done |  | Have to check
2 | Date 08-10-2021 - Time 16:07
SN | Change Request | Status | Tausif Remark | Remark
1 | Vendor & Suppliers Form - Please make the change for the Vendor & Suppliers Form as show in the mockup ( File Name : vendor-suppliers-add.html ) | Done | done
2 | Vendor & Suppliers Form - The current form is having " Type of Company" which is renamed as "Commercial Registration Type" | Done | done
3 | Vendor & Suppliers Form - In "Status *" rename Open as "Active" and Closed as "In-Active" also change in DB if its coming from DB | Not Done |  | Already mentioned in Date : 10-10-2021 - Time : 13:56 in Point Number 4
4 | Vendor & Suppliers Form - add as feild "Default Email Address" and also in the DB for customer db | Done |  | Please confirm as I have mentioned as customer db but it should be as vendor db
5 | Vendor & Suppliers Form - add this following Address ( Line 1 ) and Address ( Line 2 ) and also in the DB for customer db | Done |  | Please confirm as I have mentioned as customer db but it should be as vendor db
6 | Vendor & Suppliers Form - Rename "Postcode" as "Zip / Pin / PO Box" | Done | done
7 | Vendor & Suppliers Form - remove "Legal Entity Type" from the form and DB | Done | done
8 | Vendor & Suppliers Form - remove "Capital *" from the form and DB | Done | done
9 | Vendor & Suppliers Form - remove "Staff *" from the form and DB | Done | done
10 | Vendor & Suppliers Form - Add "TAX ID 1", "TAX ID 1", "TAX ID 1", "Import ID" & "Export ID" in the Customer creation form and in the DB also. | Done | done
11 | Vendor & Suppliers Form - Remove all "Professional ID's" from the form and DB | Done | done
12 | Vendor & Suppliers Form - Add "Business Whatsapp Number" in the Customer creation form and in the DB also. | Done | done
13 | Vendor & Suppliers Form - remove " Currency " from the form and DB | Done | done
14 | Vendor & Suppliers Form - Note : The Mock-up clearly shows what is the default selection | Done | done
15 | Note The Vendor & Suppliers Card mockup is shown in the file ( File Name : vendor-suppliers-card.html ) note : ignore the logo ist just the mockup | Done | done
16 | Note The Vendor & Suppliers Card does not hav the field "Assigned to Sales Representative" so please make sure your not adding | Done | done
1 | Date 07-10-2021 - Time 22:29
SN | Change Request | Status |  | Remark
1 | Move the User Permission , which is currently the modules, move this modules under modules tab | Done | done
2 | Disable only HRM Module for now and activate all other modules | Done | done
3 | In "Add Vendor & Supplier" there is error shown, please check that and fix it | Done | done
4 | In "Add Vendor & Supplier" the Professional ID's should not be mandatory, its marked in red* | Done | done
5 | In "Add Vendor & Supplier" --> "Prospect / Vendor & Suppliers *" the default selected should be Vendor & Suppliers | Done | done
6 | In "Add Vendor & Supplier" --> "Status *" rename Open as "Active" and Closed as "In-Active" also change in DB if its coming from DB | Done | dome
7 | In "Add Vendor & Supplier" --> "Status *" the default selected should be Open | Done | done
8 | In "Add Vendor & Supplier" --> "Country*" please add a search box as in dropdown ( call me if you don’t understand ) |  |  | It`s already there
9 | When you open/view a created invoice you can't click the left side menu or navigate other menu ( I mean you can open it ) |  |  | Breif about this
10 | Add Customer Form - Please make the change for the Add Customer Form as show in the mockup ( File Name : crm-add-customer.html ) | Done | done
11 | Add Customer Form - The current form is having " Type of Company" which is renamed as "Commercial Registration Type" | Done | done
12 | Add Customer Form - In "Status *" rename "Open" & "Close" as "Active" and Closed as "In-Active" also change in DB if its coming from DB | Not Done |  | This is not done please check if its coming from DB
13 | Add Customer Form - add as feild "Default Email Address" and also in the DB for customer db | Done | done
14 | Add Customer Form - add this following Address ( Line 1 ) and Address ( Line 2 ) and also in the DB for customer db | Done | done
15 | Add Customer Form - Rename "Postcode" as "Zip / Pin / PO Box" | Done | done
16 | Add Customer Form - remove "Legal Entity Type" from the form and DB | Done | done
17 | Add Customer Form - remove "Capital *" from the form and DB | Done | done
18 | Add Customer Form - remove "Staff *" from the form and DB | Done | done
19 | Add Customer Form - in Customer creation form "Assigned to Sales Representative" field is functional in such a way the if any staff is assigned to this company then that staff is only have rights to make Sales Invoice for this Customer
20 | Add Customer Form - Add "TAX ID 1", "TAX ID 1", "TAX ID 1", "Import ID" & "Export ID" in the Customer creation form and in the DB also. | Done | done
21 | Add Customer Form - Remove all "Professional ID's" from the form and DB | Done | done
22 | Add Customer Form - Add "Business Whatsapp Number" in the Customer creation form and in the DB also. | Done | done
23 | Add Customer Form - remove " Currency " from the form and DB | Done | done
24 | Add Customer Form - Note : The Mock-up clearly shows what is the default selection | Done | done
25 | Note The customer card will be shared tomorrow accordingly | Done |  | Customer Card Design Changes Also Done